## 1) Cover Page
NATO COMMUNICATIONS AND INFORMATION AGENCY
CO-115259-DCEP
Refresh and Sustain DCEP
(DCEP)
Part I
Schedule of Supplies and Services
VERSION 1.0
(Contract Version)

## 2) SSS
CLIN | Description | Delivery place | Delivery Date (EDC +weeks) | SOW Reference | QTY | Unit Price | Total Price | Remarks
1 | Contractor Tasks |  |  | 3
1.1 | Project Management Activities | Contractor Premises | EDC+1 week | Section 3 and 7 | Lot
1.2 | Draft Project Management Plan | NCIA Brussels | EDC+2 week | Section 3 and 7 | 1
1.3 | Final Project Management Plan | NCIA Brussels | EDC+4 week | Section 3 and 7 | 1
1.4 | PFE Integration | Contractor Premises | EDC+12 weeks | Section 3 and 7 | Lot
2 | Supply of End User Equipment
2.1 | Batch 1 | CSSC Brunsssum | EDC+12 weeks
2.1.1 | Laptops TEMPEST Level C with HDDE | CSSC Brunsssum | EDC+12 weeks | Annex-A 2.3 | 518
2.1.2 | Warranty |  | 1 Year from Acceptance
2.2 | Batch 2 | CSSC Brunsssum | EDC+13 weeks
2.2.1 | Desktops TEMPEST Level B | CSSC Brunsssum | EDC+13 weeks | Annex-A 2.4 | 259
2.2.2 | Laptops with HDDE | CSSC Brunsssum | EDC+13 weeks | Annex-A 2.3 | 250
2.2.3 | Warranty |  | 1 Year from Acceptance
2.3 | Batch 3 | CSSC Brunsssum | EDC+14 weeks
2.3.1 | Laptops with HDDE | CSSC Brunsssum | EDC+14 weeks | Annex-A 2.3 | 515
2.3.2 | Warranty |  | 1 Year from Acceptance
2.4 | Batch 4 | CSSC Brunsssum | EDC+15 weeks
2.4.1 | Laptops with HDDE | CSSC Brunsssum | EDC+15 weeks | Annex-A 2.3 | 515
2.4.2 | Warranty |  | 1 Year from Acceptance
2.5 | Batch 5 | CSSC Brunsssum | EDC+16 weeks
2.5.1 | Laptops with HDDE | CSSC Brunsssum | EDC+16 weeks | Annex-A 2.3 | 519
2.5.2 | Warranty |  | 1 Year from Acceptance
2.6 | Batch 6 | CSSC Brunsssum | EDC+17 weeks
2.6.1 | Laptops | CSSC Brunsssum | EDC+17 weeks | Annex-A 2.3 | 547
2.6.2 | Warranty |  | 1 Year from Acceptance
2.7 | Batch 7 | CSSC Brunsssum | EDC+18 weeks
2.7.1 | Laptops | CSSC Brunsssum | EDC+18 weeks | Annex-A 2.3 | 540
2.7.2 | Warranty |  | 1 Year from Acceptance
2.8 | Batch 8 | CSSC Brunsssum | EDC+19 weeks
2.8.1 | VTC Suite | CSSC Brunsssum | EDC+19 weeks | Annex-A 2.7 | 28
2.8.2 | Warranty |  | 1 Year from Acceptance
2.9 | Batch 9 | CSSC Brunsssum | EDC+20 weeks
2.9.1 | MFD | CSSC Brunsssum | EDC+20 weeks | Annex-A A.3.8 | 40
2.9.2 | Warranty |  | 1 Year from Acceptance
2.10 | Batch 10 | CSSC Brunsssum | EDC+21 weeks
2.10.1 | MFD | CSSC Brunsssum | EDC+21 weeks | Annex-A 2.6 | 40
2.10.2 | Warranty |  | 1 Year from Acceptance
2.11 | Batch 11 | CSSC Brunsssum | EDC+22 weeks
2.11.1 | MFD | CSSC Brunsssum | EDC+22 weeks | Annex-A 2.6 | 20
2.11.2 | KVM Switch | CSSC Brunsssum | EDC+22 weeks | Annex-A 2.5.3 | 1000
2.11.3 | Warranty |  | 1 Year from Acceptance
2.12 | Batch 12 | CSSC Brunsssum | EDC+23 weeks
2.12.1 | Monitor | CSSC Brunsssum | EDC+23 weeks | Annex-A 2.5.1 | 1000
2.12.2 | Warranty |  | 1 Year from Acceptance
2.13 | Batch 13 | CSSC Brunsssum | EDC+24 weeks
2.13.1 | Keyboard and Mice | CSSC Brunsssum | EDC+24 weeks | Annex-A 2.5.2 | 3692
2.13.2 | Transport Case | CSSC Brunsssum | EDC+24 weeks | Annex-A 2.3 | 3404
2.13.3 | Warranty |  | 1 Year from Acceptance
3 | Testing
3.1 | Factory Acceptance Test and Reports | Contractor Premises | EDC+10 weeks | Section 7 | Lot
3.2 | Test for the Keyed Eclypt HDDE | CSSC Brunsssum | EDC+15 weeks | Section 7 | 1
4 | Grand Total Price